## Planning Table
March 2016 TTF Planning Table
| Comms |  | Agenda/ facilitation | Confirming Participants | Logistics
Task | Responsible | A | Consulted | Informed | By (Date) | Status | Notes
Develop public messaging regarding next TTF | HP | HP | MGMT | ALL | 2015-11-13 | DONE
Contract facilitator | AH/HP | AH/HP |  | ALL | 2015-12-15 | DONE
Identify countries and participants to invite | HP | HP | MGMT | ALL | 2015-12-16 | DONE | See list from last TTF
Send initial invitations requesting willingness to send a team of three delegates | HP | HP | AM | ALL | 2015-12-16 | DONE | Agree on title then send. Request respones by Jan. 8, 2015
Scoping of existing relevant resources for TTF Topic (financing implementation of NAPs) | JP | HP | MGMT | ALL | 2015-12-23 | in progress | draft complete and circulated
Send reminder to invitees | HP | HP | AM | ALL | 2016-01-06
Contract local consultant | HP | HP | MGMT, AM | JGOV | 2016-01-06 | DONE
Confirm venue | LOG/AM/HP | HP | MGMT, JGOV, AM | ALL | 2016-01-08 | in progress | awaiting quotes
Secure hotel room block | LOG/AM/HP |  |  |  | 2016-01-08 | in progress | awaiting quotes
Invite resource persons | HP | HP |  | JGOV | 2016-01-08 |  | Consider inviting some before survey results come in?
Review responses from invitees and determine whether any countries should be replaced | MGMT |  | SC? | JGOV, AM, LOG | 2016-01-13
Send survey to participants on what to cover | HP | HP | MGMT |  | 2016-01-18
Provide visa letters to participants | AH, JGOV |  |  |  | 2016-01-22 |  | Note: Contact to consult in US embassy/mission in Jamaica?
Review survey responses and select topics to cover with rough time allocations | MGMT |  | SC? | BH | 2016-01-27
Schedule initial call with facilitator to go over topics to cover, answer questions, etc. | MGMT |  |  |  | 2016-02-03 |  | NOTE: date and time tbc pending facilitator availability
Flights booked for developing country participants | AM | HP |  | LOG | 2016-02-05
Arrange catering | LOG/AM |  |  |  | 2016-02-14
Arrange local transport | LOG/AM | HP |  | ALL | 2016-02-22
Reserve/arrange reception dinner | LOG/AM |  |  | ALL | 2016-02-22
Prepare logistics note for partoicipants | AM/HP/LOG |  |  | ALL | 2016-02-26
Send final agenda, logistics note, background material, and notes on preparation to participants | HP |  |  |  | 2016-02-29
First draft of facilitation plan (call with facilitator) | BH/HP | HP | MGMT | LOG; AM |  |  | TBC in consultation with facilitator
Second draft of facilitation plan (call with facilitator) | BH/HP |  |  | Management Team |  |  | TBC in consultation with facilitator

## Resource Persons
Resource Persons
Name | Organization | Expertise | Status
GEF
AdaptAsia
CFReady
GCF
PPCR (?)
Jan Corfee-Morlot/Michael Mullan? | OECD

## Countries
Developing Countries | Donor Countries
Albania | Germany
Bolivia | United Kingdom
Brazil | USA
Cambodia | Japan (can't attend)
Grenada
Jamaica | Secretariat Staff
Kenya | Hayley
Malawi | Anne
Peru | Christian
Philippines
South Africa | Facilitator
Togo | Blane Harvey