## Sheet1
|  | Country Contact |  |  | Nature of Support Requested |  |  | Status of Request
Country | Date | Name | Email | Organization | Advice from a Distance | In-Country Technical Support | Support to facilitate a mtg | Status
BOTSWANA | 2016-09-14 | Amanda Quigg | QuiggAJ@state.gov | US Embassy, Botswana |  |  | Training on CCA and NAP process for government officials | Complete
MOROCCO | 2016-09-21 | Naima Oumoussa | naimaoumoussa@gmail.com | Ministry of Environment, Morocco |  | Development of Morocco's NAP road map |  | Ongoing
MOROCCO | 2016-09-21 | Naima Oumoussa | naimaoumoussa@gmail.com | Ministry of Environment, Morocco |  |  | Country-level donor meeting around the NAP Road Map
ALBANIA | 2016-12-01 | Laureta Dibra | Laureta.Dibra@moe.gov.al | Ministry of Environment, Albania |  | Integrate CCA into medium-term budget process into Env and Urban Planning sectors |  | Ongoing
ALBANIA | 2016-12-01 | Laureta Dibra | Laureta.Dibra@moe.gov.al | Ministry of Environment, Albania |  | Development of adaptation-related criteria and indicators for Reg'l Dev Fund |  | Ongoing
KENYA | 2017-04-20 | Paul Kimeu | paul.kimeu@ndma.go.ke | National Drought Management Authority, Kenya | x | Sythesize lessons from various climate RL initiatives to develop a uniform M&E system for NAP implementation | County cluster mtgs; High level concluding mtg -- supplement tech support | Requested further information on technical support that would be provided (May 17)
JAMAICA | 2017-05-10 | Una May Gordon | Unamay.Gordon@megjc.gov.jm | Climate Change Division, Ministr of Economic Growth & Job Creation, Jamaica | x | Training on integration CCA into national and ministerial budgeting processes | [Training workshop] | Looking into consultants; exploring ways to reduce budget