## Sheet1
NAP Assemblies: Tracking Interest and Planning
Last updated: Feb. 8 2016
Country | Background | Last Update | Status | Next Steps
Albania | Opportunity to hold a NAP Assembly in February 2016. Discussions are planned between GIZ and EU, which is focusing on mitigation strategies and there is interest in making links with adaptation strategies. Ernest and ministry of planning interested in integrating adaptation into their work, which US is supporting. | Jan. 2016 | Awaiting US clearance to move ahead. | If US clearance received: - engage local consultant to provide logistical support - invite participants, including active donors in Albania - develop agenda and facilitation plan
Peru | Holding initial NAP meetings with stakeholders in December 2015. Laura expressed interest in learning about approaches to integrating adaptation across sectors. | Jan. 2016 | Requested update from Alvaro on how the NAP meeting went. | Follow up with Laura directly in January if no news. TTF in March (with participation from Laura, Alvaro, Adhemir) opportunity to discuss next steps.
Togo | Interested in a NAP Assembly; timeline would be early 2016 | Jan. 2016 | Awaiting confirmation from in-country mission and contacts (Germany) confirmation from US re: work in Togo | Confirm with donors and country missions
East Caribbean region | USAID and the 5Cs work regionally; Germany works in one country that is further along—use Grenada as a leader/teacher? | Feb. 2016 | Carlos Fuller at 5Cs interested and flagged interest from UNDP/Japan initiative in region as well. | Follow up with 5Cs contacts and other donors engaged around TTF, including UNDP/Japan initiative in region. TTF potential opportunity to discuss.
Tanzania | Potential longer-term opportunity. | Dec. 2015 | US and GIZ can update if country colleagues express interest
Madagascar | Potential longer-term opportunity. | Dec. 2015 | US considering providing support here; GIZ providing NAP support