## 2018
NAP Global Network Activities 2017
Legend:
Governance
Facilitating peer learning and exchange
Improving coordination
Supporting national level action
Analysis, communication and knowledge products |  | Note: Network Communications Strategy complements activities identified in work plan: specific communications activities and products are identified in the strategy (not in this work plan).
Outreach events
| 2016-12-01 | Jan | Feb | Mar |  | April |  | May |  | June |  | July | August | September | October |  | November | December
Governance
Confirm SC membership for new term (2018/19)
Steering Committee In-person Meeting (Feb 10) |  |  | x
In-Person Management Team Meeting (Feb 10) |  |  | x
Turbo TTF in Fiji (Cohorts 1 & 2)
Identification of sub-topics and key questions to address | x
Invitations, fllight bookings and logistical arrangements for participants
Survey of participants on topics of interest? (tbc) | x
Check-ins with participating countries
Development of agenda and facilitation plan
TTF Event (February 5-9, Fiji)
Data entry and analysis - Participant surveys
TTF landing page posted on website
South-South Peer Exchange Program
Assessing requests to host and coordinating placements on request
Peer learning exchange between the St Vincent and the Grenadines and Saint Lucia | [6 empty] | 20
Donor Coordination Meetings
Donor Symposium ¦ St Lucia and St Vincent | [6 empty] | x
Materials for Bilateral Development Cooperation Agencies
TBC
Country Support Hub
Assessing and responding to requests from developing countries
Seeding requests with developing countries
Nepal ¦ Technical inputs to a synthesis document
Grenada ¦ M&E
Grenada ¦ Budgeting
Cambodia ¦ Communications strategies
Morocco ¦ Country-level donor meeting for NAP Road Map
Albania ¦ Development of AD-related criteria and indicators for Reg'l Dev Fund
NAP Assemblies (further countries and dates tbc)
Saint Vincent and the Grenadines |  |  |  |  | x
Saint Lucia | [6 empty] | x
Pacific Regional Support and Engagement (Canada Funds)
Country-level support and engagement for priority countries Details tbc with Canada
Outreach events
NAP Expo (April 4-6, Bonn) | [5 empty] | 4 - 6
NDC-NAP Exchange Forum (Berlin, run by NDC Cluster, NDC-P) | [7 empty] | ?
SB 47 | [6 empty] | Apr 30 - May 10
Adaptation Futures, Cape Town | [10 empty] | 18-21
CBA12 / Regional NAP Expo ¦ TBC, likely June 2018 | [9 empty] | ? | ?
COP 24
6th Asia-Pacific Climate Change Adaptation Forum | [15 empty] | 15-19
Other outreach events tbc
Publications, Learning Materials, Knowledge Products
sNAPshot country brief ¦ Vertical integration institutional arr., Senegal
sNAPshot overview brief ¦ Communications
sNAPshot overview brief ¦ M&E
sNAPshot country brief ¦ Communications, Saint Lucia
sNAPshot overview brief ¦ Gender
sNAPshot country brief ¦ M&E, Colombia
sNAPshot country brief ¦ Gender, TBC
sNAPshot country brief ¦ Domestic public finance, Cambodia
sNAPshot overview brief ¦ Private finance
sNAPshot country brief ¦ M&E, Brazil
sNAPshot overview brief ¦ NDC-NAP linkages
sNAPshot country brief ¦ M&E, TBC
sNAPshot country brief ¦ M&E, TBC
sNAPshot country brief ¦ Gender, Kiribati
sNAPshot country brief ¦ Gender, TBC
Guidance note on NDC-NAP linkages
Webinars |  |  | Financing strategies |  |  | Gender-responsive NAP processes |  |  | TBC |  |  | TBC |  | TBC |  |  | TBC
Conflict-sensitive NAP guidance ¦ TBC
External Communications
Communications support and implementing Network communications strategy