## Template for data collection
PROGRESS ON THE IMPLEMENTATION OF ADAPTATION MEASURES_NDC AGRICULTURE RELATED INTERVENTIONS
Expected outcomes (Source:Rwanda NDC Implementation Framework) | Expected outputs (Source: Rwanda NDC Implementation Framework) | Indicators (Source: NDC 2020) | Baselines 2019/2020 | Targets (Source: Rwanda NDC Implementation Framework) | Actual status/progress since baseline & source | Sector | Focus | Projects contributing to achievement of the indicators | Implementing agencies (lead & co-implementers) | Budget (2020/21) | Budget execution (2020/21) | Progress | [6 empty] | Learning / lessons learnt
[12 empty] | Budget (2021/22) | Budget execution (2021/22) | Allocated budget (2022/23) | Actual activities | Actual outputs (2021/22 Actual Performance) | Actual outcomes | Actual impacts
Increased productivity, nutritional value and resilience through sustainable, diversified, and integrated crop, livestock, and fish production systems in a gender-responsive and climate resilient manner | Climate resilient crops developed and climate resilient livestock promoted | Number of climate resilient crop varieties developed (Not cumulative) | 47 | By 2025 and 2030, respectively, 100 and 200 climate resilient varieties will be released (based on Vision 2050) | 70 (Source: MINAGRI Annual Report, 2020/21 FY) | Agriculture | Adaptation | Development of Market Responsive plant varieties and seed systems to reduce Rwanda's dependency | RAB (lead), MINAGRI | 1150884106 | 1351683023 | 1161510482 | 1131647746 | 1429999997 | 1. Field trials including advanced yield trials and multiplication trials 2. Nurseries installed for creating new improved and climate resilient varieties 3. Data generation accompanying varieties for official release 4. Research trials on new varieties 5. Farmer's perception assessments | 69 (Source: MINAGRI Report, 2021/22) | The case studies determined that drought-tolerant crop varities helped farmers to increase production and incomes because of higher yields and planting in all seasons. (Tsinda, et al., 2022) | Local seeds that are resilient to climate change are produced and available, which is leading to higher productivity per ha at low cost of production. These seeds are based on agroecological zones. The 2022 case study determined that drought-tolerant varities help farmer cope with the climate impacts of drought and erratic rain fall. (Tsinda, et al., 2022 and discussions with MINAGRI staff). | Importance of local seeds production as one of the strategies to reduce Rwanda's dependency on seed importation
[8 empty] | RAB Competitive Research Project | RAB (lead), MINAGRI | 2197649622 | 1569263465 | 3065967701 | 1569833049 | 1881288489
|  | Percentage of farmers adopting resilient crop/ varieties | 22 (Season A) 12 (Season B) 15 (Season C) (NISR,SAS 2019) | By 2025 and 2030, respectively, 50% and 90% of farmers will be using improved seeds varieties | 35.2 (Season A) 15.6 (Season B) 30.6 (Season C) (NISR, SAS 2020) 37.1 (Season A) 17.2% (Season B) 23.8% (Season C) (NISR, SAS 2021) 33.1% (Season A) 8.7% (Season B) 26.1% (Season C) (NISR,SAS 2022) | Agriculture | Adaptation | Crop Intensification Project (CIP) | RAB (lead), MINAGRI | 11324414830.3333 | 10857192469.3333 | 16264570426.5211 | 16217197911.5211 | 11237240938 | 1. Development and dissemination of guidelines for improved seed use 2. Timely supply of improved seeds to all farmers in seasons A, B, and C 3. Training of farmers and extension agents on good agriculture practices 4. Monitoring the use of improved seeds across the country | 81.7% of large-scale farmers and 31.9% of small-scale farmers used improved seeds (Source: NISR: SAS, Season A 2022). | Increased productivity, nutritional value and resilience through sustainable, diversified, and integrated crop production systems. (No assessment so far conducted to capture the actual outcomes, this is mainly based on the feedback from MINAGRI) | Availability of food commodities in the country. (No assessment so far conducted to capture the actual impacts, this is mainly based on MINAGRI inputs) | Effective use of improved seed varieties on consolidated sites positively affects crop productivity
|  | Percentage of crossbreed livestock at national herd species | 58.5 (NISR, AHS 2017) | Under development | 965,208 crossbreeds represent 60% of total national herd species (1,607,469) for cattle (Source: NISR, AHS 2020) | Agriculture | Adaptation | Livestock Intensification Program (LIP) | RAB (lead), MINAGRI | 3408111492 | 3066525509 | 4149959548 | 4412787474 | 3003180212 | 1. Avail good quality semen and liquid nitrogen 2. Support and facilitate AI campaign 3. Train districts veterinaries on adequate AI techniques 4. Follow-up the insemination of targeted cows 5. Construction of a Bull Station 6. Cattle identification and registration in system | 487,207 crossbreeds have been registered in the system representing 34% of the total national herd species (1,417,328) (Source: Cattle Registration System) | Increased animal resource production through the use of animal breeds that are more productive. (No assessment conducted so far to capture the actual outcomes, this is mainly based on the perception from MINAGRI) | Availability of animal resources products. (No exhaustive assessment so far conducted to capture the actual impacts, this is mainly based on the current Joint Sector Review report) | Availability of quality semen and liquid nitrogen
| Climate resilient post-harvest and value addition facilities and technologies developed | Capacity of storage constructed in MT | 263,000 MT (MINAGRI Country Wide Post Harvest Facilities Dashboard 2019) | In 2030, agro-processing facilities will increase at a capacity of 1,200,000 MT | 296,770 MT (MINAGRI Annual Report, 2020/21) 316,420 MT (MINAGRI Annual Report, 2020/21) | Agriculture | Adaptation | Climate Resilient Post-Harvest and Agribusiness Support Project (PASP) | RAB (lead), MINAGRI | 818242035 | 767573434 | 0 | 0 | 0 | 1. Construction of post-harvest infrastructures (storages facilities, drying ground and shelters) 2. Purchase of sheeting/tarpaulins 3. Post-harvest awareness campaigns 4. Training of extension agents on post-harvest handling practices 5. Extend the capacity of metallic silos and warehouse | 316,420 (Source: MINAGRI Report 2021/22) | Decrease in postharvest losses for agriculture products. (No assessment so far conducted to capture the actual outcomes, this is mainly based on the perception of MINAGRI) | Increased competitiveness and value addition of diversified agricultural commodities for more inclusive domestic and international markets. (There is no assessment so far conducted to capture the actual impacts, this is mainly based on the perception of MINAGRI) | Adapt to climate change for availability of quality agriculture products
[8 empty] | Technology development for enhancement of food safety and Value addition in Agriculture | RAB (lead), MINAGRI | 545783000 | 445110582 | 887696000 | 886925168 | 250000000
[8 empty] | Sustainable Agricultural Productivity and Market linkage Project (SAPMP) | RAB (lead), MINAGRI | 265266370 | 134733538 | 823765512 | 617450348 | 1132777921
[8 empty] | National Strategic Grain Reserve (NSGR) | MINAGRI | 0 | 0 | 80000000 | 80000000 | 200000000
[8 empty] | Sustainable Agriculture Intensification and Food Security Project (SAIP) | RAB (lead), MINAGRI | 6292301414 | 5203040652 | 10185530901 | 7806342208 | 7305250050
| Crop management practices (disease prevention, diagnostic, surveillance and control) strengthened | Number of farmers using the surveillance tool (FAW Database, BXW apps etc.) | 2,000 (Final Baseline Report/Pegasys/MoE/ MINAGRI but not validated) | 9,000 farmers using surveillance tools by 2025 and 18,000 farmers by 2030 | 2,356 farmers (329 youths, 1,072 males and 975 females) mobilized to manage Fall Armyworm (FAW). 200 extension agents trained in FAW management. 4,500 farmers were registered into Banana Xanthomonas Wilt (BXW) application by farmer’s promoters, and 4,000 farms were diagnosed (Source: MINAGRI Annual Report, 2020/21 FY) | Agriculture | Adaptation | Crop Intensification Project (CIP)/ Integrated plant protection and pest management & Farmers with BXW disease application controlled and tested | RAB (lead), MINAGRI | 410855426 | 402424970 | 96040000 | 90940750 | 186000001 | 1. Mobilization campaigns on pests’ management 2. Training of frontline extension agents on Fall Armyworm (FAW) 3. Banana Xanthomonas Wilt (BXW) management using Android BXW-App 4. Surveillance for Major Pests and diseases in Banana (BXW,Thrips,Banana Bunchy top virus, etc.) 5. Training of farmers on how to identify/ diagnose, control and prevent BXW in banana farms and provide best agronomic banada practices by using BXW application. 6. Monitoring and control of pests and diseases for crops | 6,000 farmers registered into BXW application by farmer’s promoters. 5,554 BXW diagnoses via BXW App. | Increased agriculture productivity and nutritional value through pest and disease management. (No assessment so far conducted to capture the actual outcomes, this is based on the insights from MINAGRI during the consultation process) | Availability of food commodities in quantity and quality across the country. (No assessment so far conducted to capture the actual impacts, this is mainly based on the inputs of MINAGRI during the consultations) | Proper, effective and timely control of pests and deseases impacts productivity
| Sustainable land management practices (soil erosion control; landscape management) developed | Area of Land under erosion control measures and used optimally | Radical terrace: 127,339.7 ha Progressive terraces: 958,777 ha (MINAGRI Annual Report 2019/20) | 142,500 ha of land with radical terraces and 1,007,624 ha of progressive terraces by 2025 | Radical terraces: 131,056.7 ha Progressive terraces: 972,055 ha (MINAGRI Annual Report 2020/21) Radical terraces: 135,344 ha Progressive terraces: 986,276 ha (MINAGRI Annual Report 2021/22) | Agriculture | Adaptation | Government Funded Modern Irrigation (GFI) | Districts (lead), RAB, MINAGRI | 1000000000 | 1000000000 | 940000000 | 940000000 | 1200000000 | 1. Development and dissemination of guidelines for radical terraces construction 2. Mobilization of partners/stakeholders for radical and progressive terraces construction 3. Site identification and expropriation 4. Mobilization campaigns for soil erosion control activities through community works | Radical terraces: 135,343.5 ha Progressive terraces: 986,276 ha (Cumulative) (Source: MINAGRI Report 2021/22) | Job creation through the use of community approach in radical and progressive terraces constructions as a source of household income. (No assessment so far conducted to capture the actual outcomes, this is mainly based on the farmers' perception) | Increased productivity, nutritional value and resilience through climate-resilient, sustainable, diversified, and integrated crop production systems. (This is based on the perception from MINAGRI because there is no assessment so far conducted to capture the actual impacts) | Building resilience to climate change is one way to address the issue of food insecurity in the country
[8 empty] | Kayonza Irrigation and Integrated Watershed Management Project (KIIWP) | RAB (lead), MINAGRI | 851411764.7059 | 851411764.7059 | 1489970588.2353 | 1489970588.2353 | 2100000000
[8 empty] | Sustainable Agriculture Productivity and Market Linkages Project (SAPMP) | RAB (lead), MINAGRI | 85141176.4706 | 85141176.4706 | 127711764.7059 | 127711764.7059 | 1232777921
|  | Percentage of arable land (to the land area) | 59 (NISR SAS 2020) | Biological soil conservation practices of 150,000 ha by 2025 | 60% (NISR SAS, 2021) 59% (NISR SAS 2022) | Agriculture | Adaptation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1. Development of laws, orders and instructions for agriculture land protection, conservation and use | 59% Source: NISR, SAS 2022 Season A | Increased agricultural production and revenue through agricultural land protection, conservation, and effective and efficient use. (No assessment so far conducted to capture the actual outcomes, this is mainly based on the farmer's perception) | Increased availability of food commodities and revenue in a changing climate. (No assessment so far conducted to capture the actual outcomes, this is mainly based on the farmer's perception) | Effective and efficient use of agricultural land
| Irrigation and water management expanded | Number of hectares under irrigation within IWRM framework | 63,742 (MINAGRI Annual Report 2019/20) | 102,284 ha to be irrigated by 2025 200,000 ha to be irrigated by 2030 | 66,840.5 ha (MINAGRI Annual Report 2020/21) 68,126 (MINAGRI Annual Report 2021/22) | Agriculture | Adaptation | Gabiro Agri-Business Hub Project | RAB (lead), MINAGRI | 27445115894 | 26483412538 | 24080149126 | 24080149126 | 16069880874 | 1. Development of areas under marshland, hillside and small-scale irrigation 2. Rehabilitation of irrigation schemes infrastructures 3. Feasibility studies for marshland and hillside | 68,126 ha (Cumulative) (Source: MINAGRI Report 2021/22) | Increased productivity, improved yields, increased nutritional value. The case study report noted that in one area, farmers using irrigation achieved a 30% average yield increase in seasons A and B and were able to grow crops in season C. (Tsinda, et al., 2022) | Increased availabilty of food commodities in the country through efficient use of water in irrigation-related activities. The case studies demonstrated increased climate-resilience of famers because they are better able to cope with drought and erratic rain fall. (Tsinda, et al., 2022) | Reduces dependency on rain-fed agriculture and will help country achieve ambitious taregts under NST-1
[8 empty] | Buffer Project (Nasho Irrigation) | MINAGRI | 332970868 | 308970868 | 73604111 | 73604111 | 0
[8 empty] | Valorization of Rurambi Irrigation Scheme | RAB (lead), MINAGRI | 1380405425 | 1824668845 | 1283916632 | 1283916632 | 600000000
[8 empty] | Rehabilitation of Irrigation Facilities in Rwamagana District | RAB (lead), MINAGRI | 2090040769 | 1339941903 | 0 | 0 | 0
[8 empty] | Export Targeted Modern Irrigation (ETI) | RAB (lead), MINAGRI | 2524158322 | 3072541046 | 14876314570 | 11457064764 | 13526942528
[8 empty] | Government Funded Modern Irrigation (GFI) | RAB (lead), MINAGRI | 2709814222 | 4200621575 | 6550035173 | 6452513241 | 6916492070
[8 empty] | Small Scale Irrigation Technology | RAB (lead), MINAGRI | 1010000000 | 1010000000 | 1166330360 | 1126105716 | 1104439641
[8 empty] | Kayonza Irrigation and Integrated Watershed Management Project (KIIWP) | RAB (lead), MINAGRI | 4251681212.2941 | 3659967205.2941 | 10282835549.7647 | 6143247838.7647 | 2165173000
[8 empty] | W-Warufu, M-Mugesera, N-Nyamukana Irrigation Project | RAB (lead), MINAGRI | 50000000 | 50000000 | 0 | 0 | 0
[8 empty] | Rehabilitation of Bugesera Irrigation Schemes | RAB (lead), MINAGRI | 387156500 | 190066599 | 148943798 | 148943798 | 0
| Crop and livestock insurance expanded | Hectares of crops under insurance | 9,834 ha Rice: 9,477 ha Maize: 357 ha (MINAGRI annual report 2019/20) | 37,462 ha of crops insured by 2025i ncluding the following: Maize: 16,244 ha Rice: 10,322 ha Banana: 928 ha Cassava: 975 ha Beans: 278 ha Irish potato: 2,785 ha Soybeans: 278 ha French beans: 975 ha Chili: 500 ha; Tea: 4,177 ha 102,284 ha of crops insured by 2030. | Total: 23,956.3 ha Rice: 19,652.6 ha Maize: 3,861 ha Irish potatoes: 178.7 ha Green beans: 3 ha Chili: 261 ha (MINAGRI annual report 20120/21 &2021/22) | Agriculture | Adaptation | Agriculture Insurance Project | MINAGRI | 298000000 | 298000000 | 434277530 | 434185710 | 1540502906 | 1. Mobilization of farmers for crops and livestock insurance 2. Training of farmers and insurance companies | Rice: 22,047 Maize: 4730.56 Irish potatoes: 1027.6 Green beans:9.51 Chilli: 151.8 Total: 27,966 ha (Source: MINAGRI Report 2021/22) | The case studies indicated that farmers and members of cooperatives recognized that insurance helps to reduce the risks and protect from harvest losses incurred due to weather events (flooding and drought), pests and diseases. It enables farmers to cover costs and prevent losses. (Tsinda, et al., 2022) | The case tudy reported that insurance is widely recognized in Rwanda as a strategy to increase resilience to the impacts of climate change. The use of insurance has reduced the extent of risk exposure, and farmers are able to protect their livelihoods from severe production risks. (Tsinda, et al., 2022) | Helps farmers address climate change impacts and build resilient systems
|  | Number of cows under insurance | 17,373 cows (MINAGRI annual report 2019/20) | 585,792 livestock insured by 2025 Including the following: Poultry: 464,100 Piggery: 23,205 Cows: 98,487 Number of livestock insured by 2030 to be determined (assuming that the 585,792 livestock previously insured are maintained) | Cows: 24,144 Chicken: 109,630 Pigs: 2,378 (MINAGRI annual report 20120/21& 2021/22) | [10 empty] | Cows: 34,120 Chicken: 163,124 Pigs: 3,477 (Source: MINAGRI Report 2021/22)
Note on R5: Those crop varieties are developed at RAB Stations. The decrease is related to the Covid-19 effects where most of the staff were working at home during the lockdown. Varieties development-related activities need strict and close follow-up which was not easy during covid pandemic.
Note on R7: AIME TSINDA: The decrease in the percentage of farmers using improved seeds varieties is related to the increase of price (farmer’s price) from 453 Maize (2020/21) to 544 (2021/22); Soya 425 (2020/21) to 550 (2021/22) and wheat from 346 (2020/21) to 426 (2021/22).
Note on R8: Considering the data under MINAGRI, Cattle Registration System, we find that 487,207 crossbreeds have been registered in the system representing 34% of the total national herd species (1,444,776). However, the activity is still ongoing.